- General

| UKIERI Unique Reference number |  |
| --- | --- |
| Project Title | Empowerment through Knowledge: A Programme for Social Justice |
| Brief summary of the project | Broad objective of the multi partner project is to develop a new framework of training of qualifications aimed at helping the disabled people and the most disadvantaged to access employment opportunities through engagement with Skill Council, learners, employers and support organisations, generate sustainable learning and social outcomes in India and Scotland. |
| Lead partner institutions | India: Skill Council for Persons with Disability (SCPwD) United Kingdom: Glasgow Kelvin College, Scotland (GKC) |
| Project Start Date | 1st February 2018 (effectively commenced on 1st February, 2019 due to delay in receipt of funds) |
| Project End Date | 1st February 2021 |

- Activity report

| Activities planned until October 2019 (include content development, workshops, events, visits, etc) | Progress against plan (include M&E data and numbers where available and mention benefit to India and UK if applicable for the activities in this period) |
| --- | --- |
| Creation, alignment of 6 qualification Packs in the three sectors Creation of resource pack & Pool of Master trainers & Trainers Development of Apprenticeship curriculum in Hospitality Sector Employers sensitization workshops MoU’s with Employers for recruitment of persons with special needs and also their Apprenticeship Centre of Excellence Learners & Staff visits to Scotland & India | Creation/alignment of 5 QP’s have been completed 50 candidates with ID completed a pilot on the QP’s created under the Hospitality Sector, the objective was to create standards for the Skill training of Persons with Intellectual Disability. Completion of Resource pack for Trainers and Master Trainer Creation of a pool of 31 Master Trainers and 75 Trainers using the resource pack. 26 batches of Trainers trained through the Master Trainers resulting in addition of quality resource of 355 Trainers & 354 Assessors for training of candidates with special needs in the Skill Ecosystem. Certified trainers from SCPwD engaged by the affiliated Training Providers under PMKVY Skill Training of Govt of India further trained around 1500 learners with special needs. In addition, the certified Trainers of SCPwD trained 250 candidates from other skill training sources under the Department of Empowerment of Persons with Disability under Ministry of Social Justice and Empowerment, Govt of India (DEPwD-MSJE) and a few reputed NGO's associated with SCPwD. Curriculum for apprenticeship customized for the Job roles of House Keeping Attendant (Mannual Cleaning) and Front Office Associate in Hospitality Sector is available on apprenticeship portal (www.apprenticeshipindia.org) In order create awareness on the business sense of hiring persons with disability 28 Advocacy workshops have been conducted across different cities in India with participation of 929 employers’ representatives MoU’s have been signed with 112 Employers . In the absence of requisite funds for the COE, this could not be executed UK Team made 3 visits to India and the Indian team made 1 visit to UK. |

| Activities planned for next six months | With Focus on Persons with Intellectual Disability, Autism and Acid Attack Survivors, discussions have been initiated with Apparel, Gems & Jewellery and Hospitality Sector Skill Councils as well as Chamber of Industry for employers and e-meetings have been planned post 30th June, 2020 E-meetings & Sector specific virtual workshops have been planned with sectoral employers and Training Providers aiming at creation of job as well as apprenticeship opportunities for Persons with Intellectual disability. 1st virtual workshop will be held on 8th July, 2020 Customization of learning resource pack for job roles of G&J Sector Skill Council for Persons with Intellectual Disability, Autism and Acid Attack Survivors planned to be completed by 20th August 2020 Upload of 2 job roles from Hospitality Sector on National Qualification Register (Govt of India) before 30th September 2020 Conduct of 1st online webinar for trainers 15th July 2020 Sharing of major observations and recommendations of Skill training of Persons with disability with policy makers and other stakeholders to be done by 30th of July Exploring / initiating discussion for home-based apprenticeship model for persons with intellectual as well as other disability owing to the current COVID situation. To be firmed up by 30th of June 2020 |
| --- | --- |

- Project Statistics: please give below details of project beneficiaries reached till date

| Particulars | Male | Female | Total | Remark |
| --- | --- | --- | --- | --- |
| Leaders (any leader holding a ministerial profile) |  |  |  |  |
| School leaders (head of institution, head of department) |  |  |  |  |
| Government leaders (Secretary, Joint Secretary, Directors etc.) | 1 |  |  | Mr Andrew Fleming, DHC-UK, Hyderabad. |
| Community leaders (leaders at the city/district level) |  |  |  |  |
| Civil Society Organisation (CSO)/ Non-governmental Organisation (NGO) leaders | 2 |  |  | Dr Shanti Auluck Ms Neera Chawla |
| Teachers (faculties) |  |  | 31 | Master Trainers |
| Trainers |  |  | 430 | Including 354 Assessors |
| Students (India) |  |  | 1750 |  |
| Students (UK) |  |  |  |  |
| Entrepreneurs |  |  | 929 | Industry leaders through 28 Workshops |
| Institution | UK | India | Total | Remarks |
| Organisations- Tertiary (educational institutions) |  |  |  |  |
| Organisations- other (industrial, NGOs, any other) |  | 4 |  | Lemon Tree Hotels Group Muskaan NGO Dr Reddy’s Foundation American India Foundation |
| Government |  | 1 |  | National Institute for Empowerment of Persons with Intellectual Disability (NIEPID) under Ministry of Social Justice & Empowerment, Govt of India |
| Links |  |  |  |  |
| Project Outreach | Number | Details |
| Media Coverage Newspaper (Author, Name of newspaper, date, page no.) (attached scanned copy) Online coverage (Author, Name of newspaper, date, page no.) Link |  |  |
| Industry Involvement (In cash/In Kind) | For conducting 13 Workshops for Employers across 11 cities in India | Funded by Dr Reddy’s Foundation |

- Risks

| Do you foresee any risks to project delivery? | If yes, please share how you plan to mitigate those risk. |
| --- | --- |
| Indian Teams visit to Scotland for learning on best practices from Scottish models of employment and apprenticeship, SDS, Autism Society etc will undergo an unforeseen delay. Difficulties may be faced in employment and apprenticeship opportunities for learners with intellectual disability in Hospitality sector as well as a few other identified Sectors, more particularly when hospitality & travel sector seem to be the worst hit of all by Covid-19 Replicating and Scaling up skill training for Persons with ID and Autism from the major learning of the Pilot on Individuals with intellectual Disability | Online platforms/ Learning Management Systems (LMS)/ video conferencing for sharing knowledge as well as best practices is under planning Virtual workshops are being planned for the employers Draft frameworks will be prepared by capturing major observations/ recommendations under the current situation of lockdown and other restrictions. It will be shared with UK partners Draft models for online apprenticeship training for Persons with Intellectual as well as other severe disability will be explored E meetings/ dissemination workshop for aspiring organisations for Skill Training of Persons with Intellectual Disability |

- Finance

|  | British Council (In GBP) |
| --- | --- |
| Total Grant approved for your project | INR 42,24,500 |
| Total grant received till date | INR 21,12,250 |
| Grant spent till June 2020 | INR 16,51,056 |

Provide details in attached finance template.  Details attached in excel sheet

Date of submission of report: 28th June, 2020

# Footnotes

Link to UKIERI values of Complementarity, Sustainability and Mutuality of benefit)

# Text boxes

MSDE - UKIERI SKILLS THEMATIC INSTITUTIONAL PARTNERSHIPS 2016

Reporting template

Please complete this form and send this to ukieri@britishcouncil.org